## Cover Page
Nurse Call Commissioning Data
| Customer Details: | Infin8 Ipswich
43 South Street
|  | Ipswich QLD | 4305
Project Manager certifies that the configuration specified is designed to meet the site requirements, is operational and without defects at the date of signing.
Project Manager
|  | Tristan Jeremy |  | Date

## System & Network
Infin8 Ipswich - System & Network Details
System Network
Node | IP Address | Firmware | CC Firmware
Server NIC 1 | 192.168.10.100
Node 1 | 192.168.10.101 | 3.23 | 1.45
Node 2 | 192.168.10.102 | 3.23 | 1.45
Node 3 | 192.168.10.103 | 3.23 | 1.45
RS232 Module 1 | 192.168.10.131 | 1.07
Wireless Module | 192.168.10.140 | 3.14
Client Network
IP Purpose | IP Address | MAC | Comments
Server NIC 2 | 10.0.11.239
Gateway | 10.0.11.254
DNS 1 | 10.0.17.150
DNS 2 | 8.8.8.8
Licenses
Key | Certificate Number | Start Date | Concurrent Users | Modules | Unlock Code
6BBF-36B7-EB1B-B6A9-7F6F-B779 | 1397 | 2020-02-26 | 4 | DECT
Server Access
System | Username | Password
Ubuntu Server | administrator | advancecare
Users
Username | Password | Master User?
default user | default | Yes
Cablecomm | Cablecomm4433 | Yes
reports | reports1
Terminal Users
Username | Password
admin | admin
terminal | terminal
tech | tech
reports | reports1

## Nodes
Infin8 Ipswich - Nodes Configuration
Room | Node ID | Slot ID | Card Type | Port ID | Connected to Location | Patch Port | Comments
Level 2 Comms Room | 1 | 1 | AC-IPUPS |  |  |  | Power, UPS and Annunciator Card
|  | 2 | AC-IPNC |  |  |  | LAN Card
|  | 3 | AC-IPRWLS |  |  |  | Wireless Interface Card
|  | 4 | AC-IPCC | 1 | Level 1 Room 1 | L1-1 | Call Controller Card
|  |  |  | 2 | Level 1 Room 2 | L1-2
|  |  |  | 3 | Level 1 Room 3 | L1-3
|  |  |  | 4 | Level 1 Room 4 | L1-4
|  |  |  | 5 | Level 1 Room 5 | L1-5
|  |  |  | 6 | Level 1 Room 6 | L1-6
|  | 5 | AC-IPCC | 7 | Level 1 Room 7 | L1-7 | Call Controller Card
|  |  |  | 8 | Level 1 Room 8 | L1-8
|  |  |  | 9 | Level 1 Room 9 | L1-9
|  |  |  | 10 | Level 1 Room 10 | L1-10
|  |  |  | 11 | Level 1 Room 11 | L1-11
|  |  |  | 12 | Level 1 Room 12 | L1-12
|  | 6 | AC-IPCC | 13 | Level 1 Room 13 | L1-13 | Call Controller Card
|  |  |  | 14 | Level 1 Room 14 | L1-14
|  |  |  | 15 | Level 2 Room 1 | L2-1
|  |  |  | 16 | Level 2 Room 2 | L2-2
|  |  |  | 17 | Level 2 Room 3 | L2-3
|  |  |  | 18 | Level 2 Room 4 | L2-4
|  | 7 | AC-IPCC | 19 | Level 2 Room 5 | L2-5 | Call Controller Card
|  |  |  | 20 | Level 2 Room 6 | L2-6
|  |  |  | 21 | Level 2 Room 7 | L2-7
|  |  |  | 22 | Level 2 Room 8 | L2-8
|  |  |  | 23 | Level 2 Room 9 | L2-9
|  |  |  | 24 | Level 2 Room 10 | L2-10
|  | 8 | AC-IPCC | 25 | Level 2 Room 11 | L2-11 | Call Controller Card
|  |  |  | 26 | Level 2 Room 12 | L2-12
|  |  |  | 27 | Level 2 Room 13 | L2-13
|  |  |  | 28 | Level 2 Room 14 | L2-14
|  |  |  | 29 | Ground Common
|  |  |  | 30 | Ground Beacons
Level 4 Comms Room | 2 | 1 | AC-IPUPS |  |  |  | Power, UPS and Annunciator Card
|  | 2 | AC-IPNC |  |  |  | LAN Card
|  | 3 | AC-IPRWLS |  |  |  | Wireless Interface Card
|  | 4 | AC-IPCC | 1 | Level 3 Room 1 | L3-1 | Call Controller Card
|  |  |  | 2 | Level 3 Room 2 | L3-2
|  |  |  | 3 | Level 3 Room 3 | L3-3
|  |  |  | 4 | Level 3 Room 4 | L3-4
|  |  |  | 5 | Level 3 Room 5 | L3-5
|  |  |  | 6 | Level 3 Room 6 | L3-6
|  | 5 | AC-IPCC | 7 | Level 3 Room 7 | L3-7 | Call Controller Card
|  |  |  | 8 | Level 3 Room 8 | L3-8
|  |  |  | 9 | Level 3 Room 9 | L3-9
|  |  |  | 10 | Level 3 Room 10 | L3-10
|  |  |  | 11 | Level 3 Room 11 | L3-11
|  |  |  | 12 | Level 3 Room 12 | L3-12
|  | 6 | AC-IPCC | 13 | Level 3 Room 13 | L3-13 | Call Controller Card
|  |  |  | 14 | Level 3 Room 14 | L3-14
|  |  |  | 15 | Level 4 Room 1 | L4-1
|  |  |  | 16 | Level 4 Room 2 | L4-2
|  |  |  | 17 | Level 4 Room 3 | L4-3
|  |  |  | 18 | Level 4 Room 4 | L4-4
|  | 7 | AC-IPCC | 19 | Level 4 Room 5 | L4-5 | Call Controller Card
|  |  |  | 20 | Level 4 Room 6 | L4-6
|  |  |  | 21 | Level 4 Room 7 | L4-7
|  |  |  | 22 | Level 4 Room 8 | L4-8
|  |  |  | 23 | Level 4 Room 9 | L4-9
|  |  |  | 24 | Level 4 Room 10 | L4-10
|  | 8 | AC-IPCC | 25 | Level 4 Room 11 | L4-11 | Call Controller Card
|  |  |  | 26 | Level 4 Room 12 | L4-12
|  |  |  | 27 | Level 4 Room 13 | L4-13
|  |  |  | 28 | Level 4 Room 14 | L4-14
29
30
Level 6 Comms Room | 3 | 1 | AC-IPUPS |  |  |  | Power, UPS and Annunciator Card
|  | 2 | AC-IPNC |  |  |  | LAN Card
|  | 3 | AC-IPRWLS |  |  |  | Wireless Interface Card
|  | 4 | AC-IPCC | 1 | Level 5 Room 1 | L5-1 | Call Controller Card
|  |  |  | 2 | Level 5 Room 2 | L5-2
|  |  |  | 3 | Level 5 Room 3 | L5-3
|  |  |  | 4 | Level 5 Room 4 | L5-4
|  |  |  | 5 | Level 5 Room 5 | L5-5
|  |  |  | 6 | Level 5 Room 6 | L5-6
|  | 5 | AC-IPCC | 7 | Level 5 Room 7 | L5-7 | Call Controller Card
|  |  |  | 8 | Level 5 Room 8 | L5-8
|  |  |  | 9 | Level 5 Room 9 | L5-9
|  |  |  | 10 | Level 5 Room 10 | L5-10
|  |  |  | 11 | Level 5 Room 11 | L5-11
|  |  |  | 12 | Level 5 Room 12 | L5-12
|  | 6 | AC-IPCC | 13 | Level 5 Room 13 | L5-13 | Call Controller Card
|  |  |  | 14 | Level 5 Room 14 | L5-14
|  |  |  | 15 | Level 6 Room 1 | L6-1
|  |  |  | 16 | Level 6 Room 2 | L6-2
|  |  |  | 17 | Level 6 Room 3 | L6-3
|  |  |  | 18 | Level 6 Room 4 | L6-4
|  | 7 | AC-IPCC | 19 | Level 6 Room 5 | L6-5 | Call Controller Card
|  |  |  | 20 | Level 6 Room 6 | L6-6
|  |  |  | 21 | Level 6 Room 7 | L6-7
|  |  |  | 22 | Level 6 Room 8 | L6-8
|  |  |  | 23 | Level 6 Room 9 | L6-9
|  |  |  | 24 | Level 6 Room 10 | L6-10
|  | 8 | AC-IPCC | 25 | Level 6 Room 11 | L6-11 | Call Controller Card
|  |  |  | 26 | Level 6 Room 12 | L6-12
|  |  |  | 27 | Level 6 Room 13 | L6-13
|  |  |  | 28 | Level 6 Room 14 | L6-14
|  |  |  | 29 | Laundry Chute
30

## Annunciators
Infin8 Ipswich - Annunciator Configuration
Wing | Location | Device | Device ID | Node ID | Installed | Tested | Comments
Level 1 | Dining | Annunciator | 1 | 1 | Yes | Yes
| Corridor | Annunciator | 1 | 1 | Yes | Yes
Level 2 | Dining | Annunciator | 2 | 1 | Yes | Yes
| Corridor | Annunciator | 2 | 1 | Yes | Yes
Level 3 | Dining | Annunciator | 3 | 2 | Yes | Yes
| Corridor | Annunciator | 3 | 2 | Yes | Yes
Level 4 | Dining | Annunciator | 4 | 2 | Yes | Yes
| Corridor | Annunciator | 4 | 2 | Yes | Yes
Level 5 | Dining | Annunciator | 5 | 3 | Yes | Yes
| Corridor | Annunciator | 5 | 3 | Yes | Yes
Level 6 | Dining | Annunciator | 6 | 3 | Yes | Yes
| Corridor | Annunciator | 6 | 3 | Yes | Yes

## Ground Call Points
Ground Call Points Configuration
Room | Device | Part # | Node ID | Port ID | Device ID | Connected to Device | Installed | Tested | Comments
Café | Nurse Call Button | AC-IPR-CBN | 1 | 29 | 1 |  | Yes | Yes
AWC | Nurse Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
Male WC | Nurse Call Button | AC-IPR-CBN |  |  | 3 |  | Yes | Yes
Female WC | Nurse Call Button | AC-IPR-CBN |  |  | 4 |  | Yes | Yes
Beauty Salon | Nurse Call Button | AC-IPR-CBN |  |  | 5 |  | Yes | Yes
Dining | Nurse Call Button | AC-IPR-CBN |  |  | 6 |  | Yes | Yes
Fine Dining | Nurse Call Button | AC-IPR-CBN |  |  | 7 |  | Yes | Yes
Wellness | Nurse Call Button | AC-IPR-CBN |  |  | 8 |  | Yes | Yes
Training | Nurse Call Button | AC-IPR-CBN |  |  | 9 |  | Yes | Yes
Theatre | Nurse Call Button | AC-IPR-CBN |  |  | 10 |  | Yes | Yes
Front Door Wander | Beacon | AC-IPR-BCN/S | 1 | 30 | 3 |  | Yes | Yes
| Cancel Button | AC-IPR-CBC |  |  | 1 |  | Yes | Yes
Cafe Door Wander | Beacon | AC-IPR-BCN/S | 1 | 30 | 4 |  | Yes | Yes
| Cancel Button | AC-IPR-CBC |  |  | 2 |  | Yes | Yes

## Level 1 (DSU) Call Points
Level 1 (DSU) Call Points Configuration
Room | Device | Part # | Node ID | Port ID | Device ID | Connected to Device | Installed | Tested | Comments
Room 1 | Dementia Keypad | AC-IPDEM | 1 | 1 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 2 | Dementia Keypad | AC-IPDEM | 1 | 2 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 3 | Dementia Keypad | AC-IPDEM | 1 | 3 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 4 | Dementia Keypad | AC-IPDEM | 1 | 4 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 5 | Dementia Keypad | AC-IPDEM | 1 | 5 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 6 | Dementia Keypad | AC-IPDEM | 1 | 6 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 7 | Dementia Keypad | AC-IPDEM | 1 | 7 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 8 | Dementia Keypad | AC-IPDEM | 1 | 8 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 9 | Dementia Keypad | AC-IPDEM | 1 | 9 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 10 | Dementia Keypad | AC-IPDEM | 1 | 10 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 11 | Dementia Keypad | AC-IPDEM | 1 | 11 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 12 | Dementia Keypad | AC-IPDEM | 1 | 12 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 13 | Dementia Keypad | AC-IPDEM | 1 | 13 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Room 14 | Dementia Keypad | AC-IPDEM | 1 | 14 | 0 |  | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Button | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
| Room IO Module | AC-IPIO |  |  | 5 |  | Yes | Yes
| Ensuite IO Module | AC-IPIO |  |  | 6 |  | Yes | Yes
| Entry PIR | PA6805E |  |  |  | 5 - Input 1 | Yes | Yes
| Room PIR | BDL2-W12G |  |  |  | 5 - Input 2 | Yes | Yes
| Ensuite PIR | PA6805E |  |  |  | 6 - Input 1 | Yes | Yes
Dining | Nurse Call Button | AC-IPR-CBN | 1 | 12 | 7 |  | Yes | Yes
Sitting | Nurse Call Button | AC-IPR-CBN | 1 | 9 | 7 |  | Yes | Yes
Vistior WC | Nurse Call Button | AC-IPR-CBN | 1 | 4 | 7 |  | Yes | Yes

## Level 2 Call Points
Level 2 Call Points Configuration
Room | Device | Part # | Node ID | Port ID | Device ID | Connected to Device | Installed | Tested | Comments
Room 1 | Bed Call Button | AC-IPR-CBN/P | 1 | 15 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 2 | Bed Call Button | AC-IPR-CBN/P | 1 | 16 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 3 | Bed Call Button | AC-IPR-CBN/P | 1 | 17 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 4 | Bed Call Button | AC-IPR-CBN/P | 1 | 18 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 5 | Bed Call Button | AC-IPR-CBN/P | 1 | 19 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 6 | Bed Call Button | AC-IPR-CBN/P | 1 | 20 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 7 | Bed Call Button | AC-IPR-CBN/P | 1 | 21 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 8 | Bed Call Button | AC-IPR-CBN/P | 1 | 22 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 9 | Bed Call Button | AC-IPR-CBN/P | 1 | 23 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 10 | Bed Call Button | AC-IPR-CBN/P | 1 | 24 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 11 | Bed Call Button | AC-IPR-CBN/P | 1 | 25 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 12 | Bed Call Button | AC-IPR-CBN/P | 1 | 26 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 13 | Bed Call Button | AC-IPR-CBN/P | 1 | 27 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 14 | Bed Call Button | AC-IPR-CBN/P | 1 | 28 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Dining | Nurse Call Button | AC-IPR-CBN | 1 | 26 | 7 |  | Yes | Yes
Sitting | Nurse Call Button | AC-IPR-CBN | 1 | 23 | 7 |  | Yes | Yes
Visitor WC | Nurse Call Button | AC-IPR-CBN | 1 | 18 | 7 |  | Yes | Yes

## Level 3 Call Points
Level 3 Call Points Configuration
Room | Device | Part # | Node ID | Port ID | Device ID | Connected to Device | Installed | Tested | Comments
Room 1 | Bed Call Button | AC-IPR-CBN/P | 2 | 1 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 2 | Bed Call Button | AC-IPR-CBN/P | 2 | 2 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 3 | Bed Call Button | AC-IPR-CBN/P | 2 | 3 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 4 | Bed Call Button | AC-IPR-CBN/P | 2 | 4 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 5 | Bed Call Button | AC-IPR-CBN/P | 2 | 5 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 6 | Bed Call Button | AC-IPR-CBN/P | 2 | 6 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 7 | Bed Call Button | AC-IPR-CBN/P | 2 | 7 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 8 | Bed Call Button | AC-IPR-CBN/P | 2 | 8 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 9 | Bed Call Button | AC-IPR-CBN/P | 2 | 9 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 10 | Bed Call Button | AC-IPR-CBN/P | 2 | 10 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 11 | Bed Call Button | AC-IPR-CBN/P | 2 | 11 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 12 | Bed Call Button | AC-IPR-CBN/P | 2 | 12 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 13 | Bed Call Button | AC-IPR-CBN/P | 2 | 13 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 14 | Bed Call Button | AC-IPR-CBN/P | 2 | 14 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Dining | Nurse Call Button | AC-IPR-CBN | 2 | 11 | 7 |  | Yes | Yes
Sitting | Nurse Call Button | AC-IPR-CBN | 2 | 9 | 7 |  | Yes | Yes
Vistior WC | Nurse Call Button | AC-IPR-CBN | 2 | 4 | 7 |  | Yes | Yes

## Level 4 Call Points
Level 4 Call Points Configuration
Room | Device | Part # | Node ID | Port ID | Device ID | Connected to Device | Installed | Tested | Comments
Room 1 | Bed Call Button | AC-IPR-CBN/P | 2 | 15 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 2 | Bed Call Button | AC-IPR-CBN/P | 2 | 16 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 3 | Bed Call Button | AC-IPR-CBN/P | 2 | 17 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 4 | Bed Call Button | AC-IPR-CBN/P | 2 | 18 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 5 | Bed Call Button | AC-IPR-CBN/P | 2 | 19 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 6 | Bed Call Button | AC-IPR-CBN/P | 2 | 20 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 7 | Bed Call Button | AC-IPR-CBN/P | 2 | 21 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 8 | Bed Call Button | AC-IPR-CBN/P | 2 | 22 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 9 | Bed Call Button | AC-IPR-CBN/P | 2 | 23 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 10 | Bed Call Button | AC-IPR-CBN/P | 2 | 24 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 11 | Bed Call Button | AC-IPR-CBN/P | 2 | 25 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 12 | Bed Call Button | AC-IPR-CBN/P | 2 | 26 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 13 | Bed Call Button | AC-IPR-CBN/P | 2 | 27 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 14 | Bed Call Button | AC-IPR-CBN/P | 2 | 28 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Dining | Nurse Call Button | AC-IPR-CBN | 2 | 25 | 7 |  | Yes | Yes
Sitting | Nurse Call Button | AC-IPR-CBN | 2 | 23 | 7 |  | Yes | Yes
Vistior WC | Nurse Call Button | AC-IPR-CBN | 2 | 18 | 7 |  | Yes | Yes

## Level 5 Call Points
Level 5 Call Points Configuration
Room | Device | Part # | Node ID | Port ID | Device ID | Connected to Device | Installed | Tested | Comments
Room 1 | Bed Call Button | AC-IPR-CBN/P | 3 | 1 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 2 | Bed Call Button | AC-IPR-CBN/P | 3 | 2 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 3 | Bed Call Button | AC-IPR-CBN/P | 3 | 3 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 4 | Bed Call Button | AC-IPR-CBN/P | 3 | 4 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 5 | Bed Call Button | AC-IPR-CBN/P | 3 | 5 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 6 | Bed Call Button | AC-IPR-CBN/P | 3 | 6 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 7 | Bed Call Button | AC-IPR-CBN/P | 3 | 7 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 8 | Bed Call Button | AC-IPR-CBN/P | 3 | 8 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 9 | Bed Call Button | AC-IPR-CBN/P | 3 | 9 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 10 | Bed Call Button | AC-IPR-CBN/P | 3 | 10 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 11 | Bed Call Button | AC-IPR-CBN/P | 3 | 11 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 12 | Bed Call Button | AC-IPR-CBN/P | 3 | 12 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 13 | Bed Call Button | AC-IPR-CBN/P | 3 | 13 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 14 | Bed Call Button | AC-IPR-CBN/P | 3 | 14 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Dining | Nurse Call Button | AC-IPR-CBN | 3 | 11 | 7 |  | Yes | Yes
Sitting | Nurse Call Button | AC-IPR-CBN | 3 | 9 | 7 |  | Yes | Yes
Vistior WC | Nurse Call Button | AC-IPR-CBN | 3 | 4 | 7 |  | Yes | Yes

## Level 6 Call Points
Level 6 Call Points Configuration
Room | Device | Part # | Node ID | Port ID | Device ID | Connected to Device | Installed | Tested | Comments
Room 1 | Bed Call Button | AC-IPR-CBN/P | 3 | 15 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 2 | Bed Call Button | AC-IPR-CBN/P | 3 | 16 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 3 | Bed Call Button | AC-IPR-CBN/P | 3 | 17 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 4 | Bed Call Button | AC-IPR-CBN/P | 3 | 18 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 5 | Bed Call Button | AC-IPR-CBN/P | 3 | 19 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 6 | Bed Call Button | AC-IPR-CBN/P | 3 | 20 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 7 | Bed Call Button | AC-IPR-CBN/P | 3 | 21 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 8 | Bed Call Button | AC-IPR-CBN/P | 3 | 22 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 9 | Bed Call Button | AC-IPR-CBN/P | 3 | 23 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 10 | Bed Call Button | AC-IPR-CBN/P | 3 | 24 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Bed Call Button | AC-IPR-CBN/P |  |  | 3 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 3 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 11 | Bed Call Button | AC-IPR-CBN/P | 3 | 25 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 12 | Bed Call Button | AC-IPR-CBN/P | 3 | 26 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 13 | Bed Call Button | AC-IPR-CBN/P | 3 | 27 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Room 14 | Bed Call Button | AC-IPR-CBN/P | 3 | 28 | 1 |  | Yes | Yes
| Auxiliary Input | AC-DSKT2 |  |  |  | 1 | Yes | Yes
| Toilet Call Point | AC-IPR-CBN |  |  | 2 |  | Yes | Yes
| Shower Call Button | AC-SCB |  |  |  | 2 | Yes | Yes
Dining | Nurse Call Button | AC-IPR-CBN | 3 | 25 | 7 |  | Yes | Yes
Sitting | Nurse Call Button | AC-IPR-CBN | 3 | 23 | 7 |  | Yes | Yes
Vistior WC | Nurse Call Button | AC-IPR-CBN | 3 | 18 | 7 |  | Yes | Yes

## Laundry Chute
Laundry Chute Call Points Configuration
Level | Room | Device | Part # | Node ID | Port ID | Device ID | Connected to Device | Installed | Tested | Comments
Basement | Laundry Chute | Over Door Light | AC-IPODL | 3 | 29 | 2 |  | Yes | Yes
1 | Laundry Chute | Over Door Light | AC-IPODL | 3 | 29 | 2 |  | Yes | Yes
2 | Laundry Chute | Over Door Light | AC-IPODL | 3 | 29 | 2 |  | Yes | Yes
3 | Laundry Chute | Over Door Light | AC-IPODL | 3 | 29 | 2 |  | Yes | Yes
4 | Laundry Chute | Over Door Light | AC-IPODL | 3 | 29 | 2 |  | Yes | Yes
5 | Laundry Chute | Over Door Light | AC-IPODL | 3 | 29 | 2 |  | Yes | Yes
6 | Laundry Chute | Over Door Light | AC-IPODL | 3 | 29 | 2 |  | Yes | Yes
| Comms Rack | Input/Output | AC-IPIO |  |  | 1 |  | Yes | Yes | Data cut at IO

## Call Groups
Infin8 Ipswich - Call Group Configuration
Shifts
Name | Start Time | Days
Escalation Times (Minutes)
Repage Time | Primary to Secondary | Secondary to Tertiary | Tertiary | Emergency
Groups
Wing / Shift | Primary | Secondary | Tertiary | Emergency
Page All | Page All | Page All | Page All | Page All
Group Equipment
Site Group | Annuciator IDs | Equipment IDs
Page All | 0
Equipment
ID | Type | Name | Extension | IP Address
All